## Sheet1
| Function | Function Detail | Description | Recipient | Planned |  |  | Actual |  |  | Status | Supporter
[5 empty] | Hours | Start date | End date | Hours | Start date | End date
Database | Create Database |  | Read requirements and analysis. | Huy | 25 | 2021-08-06 | 2021-08-10 | 30 | 2021-08-06 | 2021-08-10 | done | Mr.Khiem Bui approved
Task | Assign task |  |  | Huy,Hau,Duc | 2 | 2021-08-10 | 2021-08-10 | 1.75 | 2021-08-10 | 2021-08-10 | done
Employee | 1.Bill Fee | 1.Create Customer | Create account friendly customer. | Hau | 1 | 2021-08-10 | 2021-08-16 | 0.75 | 2021-08-10 | 2021-08-18 | done
|  | 2.Create Order | Create new order | Hau | 5 | 2021-08-10 | 2021-08-16 | 3 | 2021-08-10 | 2021-08-18 | done
|  | 3.Insert Detail Order | Add,subtractproduct ,amount | Hau | 2 | 2021-08-10 | 2021-08-16 | 2 | 2021-08-10 | 2021-08-18 | done
|  | 4.Delete Order | Delete orders and line details when customers don't want to buy anymore. Can only be deleted when successfully logged in to the security account. And add product quantity in Output Detail to warehouse by order id, product id, input detail id, warehouse id. | Hau | 10 | 2021-08-10 | 2021-08-16 | 15 | 2021-08-10 | 2021-08-18 | done | Huy
|  | 5.Get List Product |  |  | 1 | 2021-08-10 | 2021-08-16 | 1 | 2021-08-10 | 2021-08-18 | done
|  | 6.Insert ouput | Create a delivery note when creating a successful order. | Huy | 0.5 | 2021-08-10 | 2021-08-13 | 0.5 | 2021-08-10 | 2021-08-14 | done
|  | 7. Insert ouput detail | Sell ​​old products to sell first, new products to sell later from the warehouse and subtract the quantity to the warehouse when the ouput is successful. | Huy | 20 | 2021-08-10 | 2021-08-13 | 22.5 | 2021-08-10 | 2021-08-14 | done
| 2.Inventory | 1. Create new input | Create new Receipt | Duc | 4 | 2021-08-10 | 2021-08-16 | 5 | 2021-08-10 | 2021-08-18 | done
|  | 2. Insert into input detail | Add product to input detail including product name, amount, input price, expiry date | Duc | 10 | 2021-08-10 | 2021-08-16 | 15 | 2021-08-10 | 2021-08-18 | done
|  | 3.Edit input detail | Edit product added to previous input details | Duc | 5 | 2021-08-10 | 2021-08-16 | 6 | 2021-08-10 | 2021-08-18 | done
|  | 5. Delete input detail | Delete input detail when that product is not sold | Duc | 4 | 2021-08-10 | 2021-08-16 | 5 | 2021-08-10 | 2021-08-18
|  | 4.Insert product | Add new product information when there is no product in the product table | Duc | 5 | 2021-08-10 | 2021-08-16 | 5 | 2021-08-10 | 2021-08-18 | done
|  | 5.get list inventory |  |  | 1 | 2021-08-10 | 2021-08-16 | 1 | 2021-08-10 | 2021-08-18 | done
| 3.Bill Manage | 1.Get List Order and Order detail |  | Hau | 1 | 2021-08-17 | 2021-08-21 | 2 | 2021-08-18 | 2021-08-22 | done
|  | 2.Search | Search by date | Hau | 0.5 | 2021-08-17 | 2021-08-21 | 1 | 2021-08-18 | 2021-08-22 | done
|  | 3.Delete | Delete orders and line details when customers don't want to buy anymore. Can only be deleted when successfully logged in to the security account. And add product quantity in Output Detail to warehouse by order id, product id, input detail id, warehouse id. | Hau | 4 | 2021-08-17 | 2021-08-21 | 5 | 2021-08-18 | 2021-08-22 | done | Huy
|  | 4.Get list Order |  | Hau | 1 | 2021-08-17 | 2021-08-21 | 1 | 2021-08-18 | 2021-08-22 | done
| 4.Change Shift | 1.Change shift | Change shifts between employees | Duc | 3 | 2021-08-17 | 2021-08-23 | 4 | 2021-08-19 | 2021-08-25 | done
|  | 2. Sending mail | Send an email to the shift staff and to the manager | Duc | 6 | 2021-08-17 | 2021-08-23 | 7 | 2021-08-19 | 2021-08-25 | done
|  | 3.Get list change shift |  | Duc | 1 | 2021-08-17 | 2021-08-23 | 1 | 2021-08-19 | 2021-08-25 | done
| 5.Roll Call | 1. Insert timesheets | Mark the date that the employee goes to work to calculate the salary at the end of the month | Hau | 2 | 2021-08-22 | 2021-08-22 | 5 | 2021-08-23 | 2021-08-24 | done
| 6. Update Information | 1. Update employee | Update Update Information of employee | Huy | 1 | 2021-08-14 | 2021-08-14 | 0.75 | 2021-08-14 | 2021-08-14 | done
|  | 2. Change Password |  | Huy | 1 | 2021-08-14 | 2021-08-14 | 0.75 | 2021-08-14 | 2021-08-14 | done
Manage | 1.Dashboard | 1.Create line chart | Show the sales status of the supermarket | Huy | 4 | 2021-08-15 | 2021-08-20 | 3 | 2021-08-15 | 2021-08-22 | done
|  | 2.Create bar chart | shows the top 10 best-selling products, and the top 5 most purchased loyal customers | Huy | 12 | 2021-08-15 | 2021-08-20 | 15 | 2021-08-15 | 2021-08-22 | done
|  | 3. Get list product and amount when the product is almost out of stock |  | Huy | 2 | 2021-08-15 | 2021-08-20 | 1 | 2021-08-15 | 2021-08-22 | done
|  | 4.Prepare monthly, quarterly and annual reports |  | Huy | 12 | 2021-08-15 | 2021-08-20 | 10 | 2021-08-15 | 2021-08-22 | done
|  | 5.calculate capital, sales revenue, revenue |  | Huy | 3 | 2021-08-15 | 2021-08-20 | 2 | 2021-08-15 | 2021-08-22 | done
| 2.Product | 1.Insert product | not allow duplicate name | Hau | 0.5 | 2021-08-23 | 2021-08-26 | 1 | 2021-08-25 | 2021-08-27 | done
|  | 2.Edit Product | not allow duplicate name with orthers product. Delete product when that product is not sold | Hau | 0.5 | 2021-08-23 | 2021-08-26 | 2 | 2021-08-25 | 2021-08-27 | done
|  | 3.Search | Search by name | Hau | 0.5 | 2021-08-23 | 2021-08-26 | 1 | 2021-08-25 | 2021-08-27
|  | 4.Get list product |  | Hau | 1 | 2021-08-23 | 2021-08-26 | 1 | 2021-08-25 | 2021-08-27 | done
| 3.Category | 1.Insert category | not allow duplicate name | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
|  | 2.Edit Catefory | not allow duplicate name with orthers category. Delete successfully when that category haven't product | Huy | 2 | 2021-08-21 | 2021-08-25 | 2 | 2021-08-23 | 2021-08-27 | done
|  | 3.Search | Search by name category | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
|  | 4.Get list Category |  | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
| 4.Brand | 1.Insert Brand | not allow duplicate name | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
|  | 2.Edit Brand | not allow duplicate name with orthers brand | Huy | 1 | 2021-08-21 | 2021-08-25 | 2 | 2021-08-23 | 2021-08-27 | done
|  | 3.Search | Search by name brand | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
|  | 4.Get list Brand |  | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
| 5.Supplier | 1.Insert Supplier | not allow duplicate name and phone | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
|  | 2.Edit Supplier | not allow duplicate name with orthers supplier name and phone | Huy | 1 | 2021-08-21 | 2021-08-25 | 2 | 2021-08-23 | 2021-08-27 | done
|  | 3.Search | Search by supplier's name,phone | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
|  | 4.Get list Brand |  | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
| 6.Unit | 1.Insert Unit | not allow duplicate name | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
|  | 2.Edit Supplier | not allow duplicate name with orthers unit | Huy | 1 | 2021-08-21 | 2021-08-25 | 2 | 2021-08-23 | 2021-08-27 | done
|  | 3.Get list Brand |  | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
| 7.Title | 1.Insert Title | not allow duplicate name | Huy | 1 | 2021-08-21 | 2021-08-25 | 0.5 | 2021-08-23 | 2021-08-27 | done
|  | 2.Edit Title | not allow duplicate name with orthers title | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
|  | 3.Get list Title |  | Huy | 1 | 2021-08-21 | 2021-08-25 | 1 | 2021-08-23 | 2021-08-27 | done
| 8.Bill Manager | 1.Delete Orders | Delete orders and line details when customers don't want to buy anymore. Can only be deleted when successfully logged in to the security account. And add product quantity in Output Detail to warehouse by order id, product id, input detail id, warehouse id. | Hau | 5 | 2021-08-27 | 2021-08-30 | 6 | 2021-08-28 | 2021-09-01 | done | Huy
|  | 2.Get list Order |  | Hau | 1 | 2021-08-27 | 2021-08-30 |  | 2021-08-28 | 2021-09-01 | done
| 9.Account | 1.Create account | Add new Account for new employee and not allow duplicate email and username | Huy | 1 | 2021-08-26 | 2021-08-30 | 1 | 2021-08-28 | 2021-09-01 | done
|  | 2.Edit Account | not allow duplicate email,username. And not allow change password. Lock the account when the employee has placed an order and can delete the employee when the employee does not come to accept the job | Huy | 2 | 2021-08-26 | 2021-08-30 | 1.75 | 2021-08-28 | 2021-09-01 | done
|  | 3.Search | search by name, email, username | Huy | 1 | 2021-08-26 | 2021-08-30 | 0.5 | 2021-08-28 | 2021-09-01 | done
|  | 4.Send mail | send account information and commute time to employees upon successful account creation | Huy | 5 | 2021-08-26 | 2021-08-30 | 8 | 2021-08-28 | 2021-09-01 | done
|  | 6.Get List Account |  | Huy | 1 | 2021-08-26 | 2021-08-30 | 1 | 2021-08-28 | 2021-09-01 | done
| 10.Warehouse | 1.Edit warehouse | delete expired products in warehouse | Huy | 3 | 2021-08-26 | 2021-08-30 | 2 | 2021-08-28 | 2021-09-01 | done
|  | 2.Search | Search by name,amount | Huy | 1 | 2021-08-26 | 2021-08-30 | 1 | 2021-08-28 | 2021-09-01 | done
|  | 3.Get list warehouse |  | Huy | 1 | 2021-08-26 | 2021-08-30 | 1 | 2021-08-28 | 2021-09-01 | done
| 11.Expiry | 1.Get list product expiried |  | Huy | 2 | 2021-08-26 | 2021-08-30 | 1 | 2021-08-28 | 2021-09-01 | done
Test | Test Project | Test and Fix |  | Huy,Hau,Duc | 30 | 2021-08-31 | 2021-08-04 | 35 | 2021-09-01 | 2021-09-05 | done
Document | Write Document |  |  | Duc | 6 | 2021-08-06 | 2021-08-06 | 8 | 2021-08-06 | 2021-08-06 | done
| Report Excel |  |  | Huy | 6 | 2021-08-06 | 2021-08-06 | 6 | 2021-08-06 | 2021-08-06 | done
[6 empty] | Planed |  |  | Actual
[6 empty] | Total hours: | 235.5 |  | Total hours: | 267.25
[6 empty] | Start date: | 2021-08-06 |  | Start date: | 2021-08-06
[6 empty] | End date: | 2021-09-09 |  | End date: | 2021-09-09